## Settings
Settings | [10 empty] | Gantt Chart
Project Details |  |  | Project Role Types |  |  |  | Project Team
| Project Title | Demo Project |  | Role | Code | # |  | Name | Role | #
|  |  |  | Project Management | PM | 1 |  | A. Moreno | Project Management | PM
| Project Manager: | A. Moreno |  | Coding | COD | 2 |  | C. Miller | Coding | COD
|  |  |  | Design | DES | 1 |  | M. Suarez | Coding | COD
| Project Priority | High |  | Marketing | MAR | 1 |  | S. Anthony | Marketing | MAR
|  |  |  | Finance | FIN | 1 |  | J. Fontaine | Design | DES
[8 empty] | W. Smith | Finance | FIN

## Gantt
|  | Demo Project | [19 empty] | Project Timespan: | [5 empty] | 2023-05-17 |  |  |  | - | 2023-06-26 |  |  |  | - | (29) |  |  |  |  | Project Manager: | [5 empty] | A. Moreno |  |  |  |  | Settings
|  | Input Column | [6 empty] | Auto Stage Ind.Start |  | =MIN(ITEMS_START) | [10 empty] | Color By | [7 empty] | Display | [7 empty] | Show Progress | [15 empty] | Highlight
|  | Calculated Column | [6 empty] | Auto Stage Workdays |  | =NETWORKDAYS(plan_start; MAX(ITEMS_END)) | [10 empty] | Project Structure | [7 empty] | Plan | [7 empty] | Yes | [15 empty] | 2023-05-31
|  | Snapshot Column | [6 empty] | Auto Stage % |  | =SUM(ITEMS_PERCENT*ITEMS_WORKDAYS)/SUM(ITEMS_WORKDAYS)
[9 empty] | Unicode Icons |  | Type Options
[9 empty] | ⚠ - ◆ - ⚑ - ↖ - ↙ |  | S(Stage)-T(task)-M(Milestone)
[9 empty] | Actual Plan | [9 empty] | Base Plan |  | Today | 2023-05-18 | 2023-05-19 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-03 | 2023-07-04 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-28 | 2023-07-31 | 2023-08-01 | 2023-08-02 | 2023-08-03
[9 empty] | Updated on: | [9 empty] | Saved on: |  | 3
| Ids |  |  | Item Details |  |  |  |  | 2023-05-15 | [9 empty] | 2023-05-08
color codes | Id | s id | r id | Type | Description | Role | Team Member | ⚠ | Ind. Start | Ind. End | dep. Id | dep. Item |  | dep. conn | dep. lag | Work Days | Start | End | Start | End | % | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J
101 | 1 | 1 | -1 | S | Planning |  |  | ⚠ | 2023-05-17 |  |  |  |  | FS |  | 10 | 2023-05-17 | 2023-05-30 | 2023-05-10 | 2023-05-23 | 75% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 2 | 1 | 1 | T | Task P1 | PM | A. Moreno |  | 2023-05-17 |  |  |  |  | FS |  | 5 | 2023-05-17 | 2023-05-23 | 2023-05-10 | 2023-05-16 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 3 | 1 | 2 | T | Task P2 | COD | C. Miller | ⚠ |  |  | 2 | ↖ | (T)Task P1 | FS |  | 3 | 2023-05-24 | 2023-05-26 | 2023-05-17 | 2023-05-19 | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 4 | 1 | 5 | T | Task P3 | FIN | W. Smith |  |  |  | 3 | ↖ | (T)Task P2 | FS |  | 2 | 2023-05-29 | 2023-05-30 | 2023-05-22 | 2023-05-23 | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 5 | 1 | 4 | M | Milestone I | MAR | S. Anthony | ⚠ |  |  | 4 | ↖ | (T)Task P3 | FF |  |  | 2023-05-30 | 2023-05-30 | 2023-05-23 | 2023-05-23 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 6 | 2 | -1 | S | Implementation |  |  |  | 2023-05-31 |  |  |  |  | FS |  | 10 | 2023-05-31 | 2023-06-13 | 2023-05-24 | 2023-06-06 | 12.5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 7 | 2 | 2 | T | Task I1 | COD | M. Suarez |  |  |  | 1 | ↖ | (S)Plannin… | FS |  | 5 | 2023-05-31 | 2023-06-06 | 2023-05-24 | 2023-05-30 | 25% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 8 | 2 | 2 | T | Task I2 | COD | M. Suarez |  |  |  | 7 | ↖ | (T)Task I1 | FS |  | 3 | 2023-06-07 | 2023-06-09 | 2023-05-31 | 2023-06-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 9 | 2 | 1 | T | Task I3 | PM | A. Moreno |  |  |  | 8 | ↖ | (T)Task I2 | FS |  | 2 | 2023-06-12 | 2023-06-13 | 2023-06-05 | 2023-06-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 10 | 2 | 3 | M | Milestone II | DES | J. Fontaine |  |  |  | 9 | ↖ | (T)Task I3 | FF |  |  | 2023-06-13 | 2023-06-13 | 2023-06-06 | 2023-06-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 11 | 3 | -1 | S | Rollout Prep. |  |  |  | 2023-05-30 |  |  |  |  | FS |  | 11 | 2023-05-30 | 2023-06-13 | 2023-05-23 | 2023-06-06 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 12 | 3 | 2 | T | Task RP1 | COD | M. Suarez |  |  |  | 13 | ↙ | (T)Task RP… | SF |  | 5 | 2023-05-30 | 2023-06-05 | 2023-05-23 | 2023-05-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 13 | 3 | 2 | T | Task RP2 | COD | C. Miller |  |  |  | 14 | ↙ | (T)Task RP… | SF |  | 4 | 2023-06-06 | 2023-06-09 | 2023-05-30 | 2023-06-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 14 | 3 | 4 | T | Task RP3 | MAR | S. Anthony |  |  |  | 15 | ↙ | (M)Milesto… | FF |  | 2 | 2023-06-12 | 2023-06-13 | 2023-06-05 | 2023-06-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 15 | 3 | 1 | M | Milestone IV | PM | A. Moreno |  |  |  | 6 | ↖ | (S)Impleme… | FF |  |  | 2023-06-13 | 2023-06-13 | 2023-06-06 | 2023-06-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 16 | 4 | -1 | S | Rollout |  |  |  | 2023-06-14 |  |  |  |  | FS |  | 9 | 2023-06-14 | 2023-06-26 | 2023-06-07 | 2023-06-19 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 17 | 4 | 1 | T | Task R1 | PM | A. Moreno |  |  |  | 11 | ↖ | (S)Rollout… | FS |  | 3 | 2023-06-14 | 2023-06-16 | 2023-06-07 | 2023-06-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 18 | 4 | 5 | T | Task R2 | FIN | W. Smith |  |  |  | 17 | ↖ | (T)Task R1 | FS |  | 3 | 2023-06-19 | 2023-06-21 | 2023-06-12 | 2023-06-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 19 | 4 | 5 | T | Task R3 | FIN | W. Smith |  |  |  | 18 | ↖ | (T)Task R2 | FS |  | 3 | 2023-06-22 | 2023-06-26 | 2023-06-15 | 2023-06-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 20 | 4 | 3 | M | Milestone V | DES | J. Fontaine |  |  |  | 19 | ↖ | (T)Task R3 | FF |  |  | 2023-06-26 | 2023-06-26 | 2023-06-19 | 2023-06-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1 | 21 | -1 | -1 | [10 empty] | FS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1 | 22 | -1 | -1 | [10 empty] | FS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1 | 23 | -1 | -1 | [10 empty] | FS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1 | 24 | -1 | -1 | [10 empty] | FS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1 | 25 | -1 | -1 | [10 empty] | FS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1 | 26 | -1 | -1 | [10 empty] | FS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0